## Sheet1
Task ID | Task Name | Assigned | Task Status | Exepected Time To Finish | Actual Time To Finish
1 | MCAL_I2C_DESIGN | Bassel Yasser | 100 | 30 minutes | 1 hour
2 | MCAL_I2C_IMPLEMENTATION | Bassel Yasser | 100 | 30 minutes | 30 minutes
3 | MCAL_I2C_TEST | Bassel Yasser | 100 | 15 minutes | 1 hour
4 | MCAL_DIO Module | Bassel Yasser | 100 | 15 minutes | 15 minutes
5 | MCAL_TIMER2_DESIGN | Bassel Yasser | 100 | 30 minutes | 30 minutes
6 | MCAL_TIMER2_IMPLEMENTATION | Bassel Yasser | 100 | 30 minutes | 45 minutes
7 | MCAL_TIMER2_TESTING | Bassel Yasser | 100 | 15 minutes | 30 minutes
8 | ECUAL_HTIMER2 | Bassel Yasser | 100 | 10 minutes | 10 minutes
9 | ECUAL_BUTTON Module | Bassel Yasser | 100 | 15 minutes | 15 minutes
10 | ECUAL_LCD Module | Bassel Yasser | 100 | 15 minutes | 15 minutes
11 | CARD_terminalPinGet API | Bassel Yasser | 100 | 30 minutes | 45 minutes
12 | ATM_ENTER/ZERO_Button API | Bassel Yasser | 100 | 1 hour | 2 hours
13 | MCAL_USART_DESIGN | Sharpel Malak | 100 | 1 hour | 1 hour
14 | MCAL_USART_IMPLEMENTATION | Sharpel Malak | 100 | 1 hour | 90 minutes
15 | MCAL_USART_TESTING | Sharpel Malak | 100 | 30 minutes | 30 minutes
16 | MCAL_EXTINT Module | Sharpel Malak | 100 | 10 minutes | 10 minutes
17 | ECUAL_KEYPAD Module | Sharpel Malak | 100 | 10 minutes | 10 minutes
18 | ECUAL_HEXTINT | Sharpel Malak | 100 | 10 minutes | 10 minutes
19 | ECUAL_HUSART | Sharpel Malak | 100 | 15 minutes | 15 minutes
20 | Card_terminalPanGet API | Sharpel Malak | 100 | 30 minutes | 30 minutes
21 | ATM_Get_pin API | Sharpel Malak | 100 | 30 minutes | 1 hour
22 | ATM_get_amount_left API | Sharpel Malak | 100 | 1 hour | 3 hours
23 | MCAL_TIMER0 Module | Alaa Hisham | 100 | 10 minutes | 10 minutes
24 | MCAL_SPI_DESIGN | Alaa Hisham | 100 | 15 minutes | 15 minutes
25 | MCAL_SPI_IMPLEMENTATION | Alaa Hisham | 100 | 30 minutes | 30 minutes
26 | MCAL_SPI_TESTING | Alaa Hisham | 100 | 10 minutes | 10 minutes
27 | ECUAL_HSPI_DESIGN | Alaa Hisham | 100 | 30 minutes | 1 hour
28 | ECUAL_HSPI_IMPLEMENTATION | Alaa Hisham | 100 | 1 hour | 1 hour
29 | ECUAL_HSPI_TESTING | Alaa Hisham | 100 | 1 hour | 3 hours
30 | ECUAL_BUZZER Module | Alaa Hisham | 100 | 5 minutes | 5 minutes
31 | CARD_MatchPINs API | Alaa Hisham | 100 | 15 minutes | 15 minutes
32 | ATM_GetCardData API | Alaa Hisham | 100 | 15 minutes | 15 minutes
33 | ATM_ApprovedCard API | Alaa Hisham | 100 | 30 minutes | 30 minutes
34 | ECUAL_EEPROM_DESIGN | Sherif Khedr | 100 | 20 minutes | 3 hours
35 | ECUAL_EEPROM_IMPLEMENTATION | Sherif Khedr | 100 | 2 hours | 6 hours
36 | ECUAL_EEPROM_TESTING | Sherif Khedr | 100 | 2 hours | 8 hours
37 | ATM_PIN_checkPinMatching API | Sherif Khedr | 100 | 20 minutes | 20 minutes
38 | ATM_deinitAtm API | Sherif Khedr | 100 | 10 minutes | 10 minutes
39 | CARD_SaveCardData API | Sherif Khedr | 100 | 1 hour | 6 hours
40 | CARD_READCardData API | Sherif Khedr | 100 | 1 hour | 6 hours
41 | ATM_DATABASE_CHECKING Module | Sprinters | 100 | 30 minutes | 30 minutes
42 | INTEGRATION | Sprinters | 100 | 3 hour | 1 hour
43 | SIMULATION_DEBUGGING | Sprinters | 100 | 2 hours | 2 days
44 | HARDWARE_DEBUGGING | Sprinters | 85 | 2 hours | 4 days and counting